## Project_Plan
Project Name: Holiday Assessment
Module	Start Date	End Date	Estimated Hours	Actual Hours	Developer	Status
Modules/Tasks					Status
Milestone 1	23/12/2024	27/12/2024
Sprint #1 - Project setup	23/12/2024	24/12/2024	8
Project setup for frontend:			4
React with Type-script React Query and UI packages
Common components setup
Eslint setup
Project setup for backend:			4
API module ( Backend setup )
Common Module setup
Configuration and enviornment setup
Sprint #2 – User Model, Authentication, Authorization, and Intial user interactions pages.	24/12/2024	26/12/2024	14
User Authentication and Sign-Up			3
User Model Design
Middleware for JWT authentication
Authentication(APIs)			4
API for User Sign-Up
API for User Login
API for Change Password
Frontend			7
Login and Signup page Design
Login and Signup functionality
User Dashoard UI Design

Sprint #3 – User Profile Section	26/12/2024	27/12/2024	14
Backend			8
API for Add user details
API for Show user details
API for Update user details
Multer integration for profile photo
Frontend:			6
Update/Add user details UI Design
Update/Add user details UI functionality
Milestone 2	27/12/2024	04/12/2024
Sprint #4 – Preference Section	27/12/2024	29/12/2024	11
Backend			5
API for add preference
API for show preference
API for update preference
Frontend			6
Preference section UI Design
Preference section UI Functionality

Sprint #5 – Invite Friend Section	30/12/2024	04/01/2025	20
Backend			10
Friends Model Design
API for Invite Friend
API for Listing Friends
Frontend			10
Invite Friend UI Design
Invite Friend UI Functionality
List Friends UI Desing and Functionality

Milestone 3	04/01/2025	08/01/2025
Sprint #6- Waves Section	04/01/2025	08/01/2025	30
Creat Waves:-			18
Backend			8
Wave model design
API for create wave
Handling images and video upload
Frontend:			10
Create waves UI Design
Adding text editor for wave description
Create waves UI functionality
Waves Comment:-			12
Backend			7
Comment model design
API for Adding comments
API for Show comments
Frontend:			5
Comment UI Design and functionality

Milestone 4: Admin Section	09/01/2025	13/01/2025
Sprint #7 – Admin Login and Signup Section	09/01/2025	11/01/2025	20
Backend			8
Admin Model Design
Middleware for admin authentication
API for Admin Signup
API for Admin Login
Frontend			6
Login and Signup page Design
Login and Signup functionality

Admin Dashoard UI Design	12/01/25	13/01/25	6

Sprint #8 – Admin Dashboard	13/01/2025	17/01/2025	35
Backend	13/01/2025	15/01/2025	15
API for admin dashboard
API for manage users
API for manage Waves

Frontend	15/01/25	17/01/25	20
UI and Functionality for manage users
UI and Functionality for manage Waves
PDF and csv export

## Milestone_Schedule
Project Release Plan
Milestone No	Sprint	No. of resources	Start Date	End Date	Release No	Milestone Acceptance date	Actual hrs burnt	Status	Acceptance Date
1	2	2	26 Aug 24	8 Sep 24	ER1	16 Sep 24
2	2	2	9 Sep 24	22 Sep 24	ER2	30 Sep 24
3	2	2	23 Sep 24	6 Oct 24	ER3	14 Oct 24
4	2	2	7 Oct 24	20 Oct 24	ER4	28 Oct 24
5	2	2	21 Oct 24	3 Nov 24	ER5	7 Nov 24

## Summary
Project Start Date	26 Aug 24
Actual End Date	31 Oct 24
Sales Person	⁠Vishal Sagar Shahi

Revision History
Date	Author	Changes Details	Reference
23 Aug 24	Gaurav Sexena

Resource Allocation
Name	Role On Project	Alignment Date	Resource Released Date
Jashan Dhiman	Developer	22 Aug 24
Bhushan Sharma	Developer	22 Aug 24

## Ghant_chart
Gantt Chart
Project Name:	Eye-Refer				Project Start Date		26 Aug 24
Project Owner:	Jashan dhiman				Project End Date		31 Oct 24
Project Lead :	Gaurav Saxena
				26 Aug 24	2 Sep 24	9 Sep 24	16 Sep 24	23 Sep 24	30 Sep 24	7 Oct 24	14 Oct 24	21 Oct 24	28 Oct 24
				M1		M2		M3		M4		M5
	Resources	Start date	End date	WEEK 1	WEEK 2	WEEK 3	WEEK 4	WEEK 5	WEEK 6	WEEK 7	WEEK 8	WEEK 9	WEEK 10
Admin / Web / Api	Jashan Dhiman	26 Aug 24		40	40	40	40	40	40	40	40
	Bhushan Sharma	26 Aug 24		40	40	40	40	40	40	40	40
Desginer	⁠Yashpal Chaudhary	26 Aug 24	31/01/24	40	20	20

	Collection
	Deliverables
	Acceptance
	Review